## Website
Name | Day | Time From | Time To | Done-did List | Working Hours
Jingyu | Monday | 13:30 | 14:30 | Project planning and discussion | 1:00
Amirhossein | Monday | 13:30 | 14:30 | Project planning and discussion | 1:00
Curtis | Monday | 13:30 | 14:30 | Project planning and discussion | 1:00
Zachary | Monday | 13:30 | 14:30 | Project planning and discussion | 1:00
Gang | Monday | 13:30 | 14:30 | Project planning and discussion | 1:00
Jingyu | Monday | 21:30 | 23:30 | Build contact page | 2:00
Jingyu | Tuesday | 9:00 | 12:00 | Fix contact page style | 3:00
Amirhossein | Tuesday | 9:00 | 12:00 | Build skills page | 3:00
Curtis | Tuesday | 9:00 | 12:00 | Build education page | 3:00
Zachary | Tuesday | 9:00 | 12:00 | Build index page | 3:00
Gang | Tuesday | 9:00 | 11:00 | Build work experience page | 2:00
Jingyu | Tuesday | 12:30 | 16:30 | Fix contact page and modify style | 4:00
Amirhossein | Tuesday | 12:30 | 15:00 | Fix skills page | 2:30
Curtis | Tuesday | 12:30 | 15:00 | Fix education page | 2:30
Zachary | Tuesday | 12:30 | 16:00 | Fix intex page and modify all style | 3:30
Gang | Tuesday | 12:00 | 12:30 | Build work experience page | 0:30
Jingyu | Tuesday | 18:30 | 21:00 | Modify all page | 2:30
Name | Total Working Hours |  |  | Guide
Jingyu | 12:30 |  | 1 | Select a cell and insert table row above
Amirhossein | 6:30 |  | 2 | Fill down each cell
Curtis | 6:30 |  | 3 | Enter the 24-hour time.(ex:15:00)
Zachary | 7:30 |  | 4 | On Working Hour cell, Changing the Format cells from General to Time
Gang | 3:30

## Excel
Name | Day | Time From | Time To | Done-did List | Working Hours
Jingyu | Monday | 14:00 | 16:30 | Making Workload excel file | 2:30
Jingyu | Monday | 20:30 | 21:30 | Add doughnut chart and data | 1:00
Amirhossein |  |  |  |  | 0:00
Curtis |  |  |  |  | 0:00
Zachary |  |  |  |  | 0:00
Gang | Tuesday | 11:00 | 12:00 | Modify the Excel to add the work on the Word. | 1:00
Name | Total Working Hours |  |  | Guide
Jingyu | 3:30 |  | 1 | Select a cell and insert table row above
Amirhossein | 0:00 |  | 2 | Fill down each cell
Curtis | 0:00 |  | 3 | Enter the 24-hour time.(ex:15:00)
Zachary | 0:00 |  | 4 | On Working Hour cell, Changing the Format cells from General to Time
Gang | 1:00

## Visio-Word
Name | Day | Time From | Time To | Done-did List | Working Hours
Jingyu |  |  |  |  | 0:00
Amirhossein |  |  |  |  | 0:00
Curtis | Tuesday | 13:00 | 14:00 | Making Visio file | 1:00
Zachary | tuesday | 15:00 | 15:30 | working on visio | 0:30
Gang | Tuesday | 13:00 | 16:30 | Making Visio file | 3:30
Name | Total Working Hours |  |  | Guide
Jingyu | 0:00 |  | 1 | Select a cell and insert table row above
Amirhossein | 0:00 |  | 2 | Fill down each cell
Curtis | 1:00 |  | 3 | Enter the 24-hour time.(ex:15:00)
Zachary | 0:30 |  | 4 | On Working Hour cell, Changing the Format cells from General to Time
Gang | 3:30

## PowerPoint
Name | Day | Time From | Time To | Done-did List | Working Hours
Jingyu |  |  |  |  | 0:00
Amirhossein |  |  |  |  | 0:00
Curtis |  |  |  |  | 0:00
Zachary |  |  |  |  | 0:00
Gang | Tuesday | 19:00 | 20:00 |  | 1:00
Name | Total Working Hours |  |  | Guide
Jingyu | 0:00 |  | 1 | Select a cell and insert table row above
Amirhossein | 0:00 |  | 2 | Fill down each cell
Curtis | 0:00 |  | 3 | Enter the 24-hour time.(ex:15:00)
Zachary | 0:00 |  | 4 | On Working Hour cell, Changing the Format cells from General to Time
Gang | 1:00

## Total
Name | Website | Excel | Visio | PowerPoint | Total
Jingyu | 12:30 | 3:30 | 0:00 | 0:00 | 16:00
Amirhossein | 6:30 | 0:00 | 0:00 | 0:00 | 6:30
Curtis | 6:30 | 0:00 | 1:00 | 0:00 | 7:30
Zachary | 7:30 | 0:00 | 0:30 | 0:00 | 8:00
Gang | 3:30 | 1:00 | 3:30 | 1:00 | 9:00
Work time per item | 36:30 | 4:30 | 5:00 | 1:00